## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Animesh Sawant
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## Project Schedule
IAC Internship Program 2023 - Web Development Project Schedule
|  | PROJECT START DATE | 2023-07-31
|  | Display Week Sr No | 1 | [10 empty] | 2023-07-31 | [6 empty] | 2023-08-07 | [6 empty] | 2023-08-14 | [6 empty] | 2023-08-21 | [6 empty] | 2023-08-28 | [6 empty] | 2023-09-04 | [6 empty] | 2023-09-11 | [6 empty] | 2023-09-18 | [6 empty] | 2023-09-25 | [5 empty] | 2023-10-01
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | time axis 2023-07-31 to 2023-10-01
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Assigned to | Start Date | End Date | Status | M | T | W | T | F | S | time axis 2023-07-31 to 2023-10-01
1 | Week 1 | Project Initiation |  | Prasad Pathare |  |  | Completed
1.2 |  |  | Identify given problem |  | 01-08-20223 | 2023-08-04 | Completed
1.3 |  |  | Finalize on the problem statement |  | 2023-08-05 | 2023-08-06 | Completed
1.4 |  |  | Create a project charter |  | 2023-08-08 | 2023-08-09 | Completed
1.5 |  |  | Requirement Elicitation |  | 2023-08-13 | 2023-08-18 | Completed
1.6 |  |  | Software Requirements Specification Document |  | 2023-08-19 | 2023-08-20 | Completed
2 | Week 2 | Planning |  | Prasad Pathare |  |  | Completed
2.1 |  |  | Technologies to be used |  | 2023-08-22 | 2023-08-23 | Completed
2.2 |  |  | Design |  | 2023-08-24 | 2023-08-25
2.2 |  |  | Project Scope |  | 2023-08-26 | 2023-08-26 | Completed
2.3 |  |  | Use Of IDE |  | 2023-08-27 | 2023-08-27 | Completed
3 | Week 3 | Execution |  | Animesh Sawant |  |  | Completed
3.1 |  |  | Finalize design |  | 2023-08-29 | 2023-08-29 | Completed
3.2 |  |  | Build |  | 2023-08-30 | 2023-08-30 | Completed
3.3 |  |  | finalizing HTML skeleton |  | 2023-08-31 | 2023-08-31 | Completed
3.4 |  |  | Making Componenets |  | 2023-09-01 | 2023-09-01 | Completed
3.5 | [6 empty] | Completed
3.6 |  |  | Adding style sheet |  | 2023-09-02 | 2023-09-08 | Completed
3.7 |  |  | Gathering College data |  | 2023-09-03 | 2023-09-09 | Completed
3.8 |  |  | Database setup |  | 2023-09-04 | 2023-09-10 | Completed
3.9 |  |  | Input gathered Data sets |  | 2023-09-05 | 2023-09-11 | Completed
3.1 |  |  | Error Solving |  | 2023-09-06 | 2023-09-14 | Completed
3.11 | [6 empty] | Completed
3.2.1.3 Model Training
Training Various Models
3.2.1.4 Model Evaluation and Prediction
Evaluating Test Data on Trained ML model
3.2.2 Graduation Year
Exploratory Data Analysis
Devising Equation to Predict Graduation Year
4 | Week 4 | Testing |  | Prasad Pathare |  |  | Completed
4.1 |  |  | Manual testing |  | 2023-09-15 | 2023-09-19 | Completed
4.2 |  |  | Error find |  | 2023-09-16 | 2023-09-20 | Completed
4.3 |  |  | Evaluating Test Data |  | 2023-09-17 | 2023-09-21 | Completed
4.4 |  |  | Evaluating the time diffrenece for loading Webapp |  | 2023-09-18 | 2023-09-22 | Completed
4.5 |  |  | Changes in Media Queries |  | 2023-09-19 | 2023-09-23 | Completed
4.6 |  |  | Making more Responsive webapp |  | 2023-09-20 | 2023-09-24 | Completed
4.7 |  |  | Devising Equation to Predict Graduation Year |  | 2023-09-21 | 2023-09-25 | Completed
5 | Week 5 | Closure |  | Prasad Pathare |  |  | Completed
5.1 |  |  | Project Closure |  | 2023-09-27 | 2023-09-29 | Completed
5.2
Note on F7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you